Project Scope Management Plan

Project Name: HealthFirst Care Improvement Initiative

1. Project Scope Statement

1.1 Project Objectives

The primary objectives of this project are:

- Reduce patient wait times by at least 30%

- Improve appointment scheduling efficiency and accuracy

- Enhance communication between departments and stakeholders

- Optimize resource allocation (doctors, rooms, equipment)

- Implement real-time notifications for patients and staff

- Improve patient satisfaction and operational transparency

1.2 In-Scope Activities

The project will include:

Scheduling & Patient Management

- Automating appointment scheduling system

- Integrating online and offline booking channels

- Eliminating double bookings and scheduling conflicts

Resource Optimization

- Implementing real-time resource tracking dashboards

- Monitoring doctor availability, room usage, and equipment allocation

Communication Enhancements

- Developing real-time notification systems (SMS/email alerts)

- Improving inter-department communication workflows

Data & Analytics

- Implementing reporting dashboards for:

  - Wait times

  - Resource utilization

  - Patient flow

System Integration

- Integrating scheduling, billing, and patient record systems

- Enhancing usability of hospital IT systems

1.3 Out-of-Scope Activities

The following are explicitly excluded:

- Hospital construction or infrastructure expansion

- Hiring or restructuring clinical staff

- Replacement of core clinical systems (e.g., diagnostic tools)

- Major overhaul of billing systems (only integration included)

- Non-operational improvements (e.g., branding, marketing campaigns)

1.4 Constraints

- Budget Constraints: Limited funding for IT upgrades and tools

- Time Constraints: Project must be completed within 6–9 months

- Regulatory Constraints: Compliance with healthcare data regulations (e.g., HIPAA or local equivalents)

- Technical Constraints: Legacy system compatibility and integration limitations

- Resource Constraints: Limited availability of hospital staff for workshops/testing

1.5 Assumptions

- Stakeholders will be available for regular reviews and feedback

- Existing hospital data is accurate and accessible

- IT infrastructure can support system integration

- Staff will adopt new systems after training

- No major policy or regulatory changes during the project

Scope Management Plan

2.1 Scope Change Request Process

- Submit formal change request document

- Log request in Change Register

- Conduct impact analysis:

  - Cost

  - Time

  - Resources

- Review by Project Manager and stakeholders

- Decision:

  - Approve / Reject / Defer

- Update scope baseline and project documents

- Communicate changes to all stakeholders

2.2 Approval Criteria

Scope changes will be approved based on:

- Alignment with project objectives

- Impact on patient care and efficiency

- Budget availability

- Timeline feasibility

- Regulatory compliance

2.3 Scope Monitoring & Validation

Monitoring

- Weekly progress tracking against WBS

- KPI tracking (wait time, scheduling efficiency)

- Regular stakeholder meetings

Validation

- Validation against:

  - Business Requirements Document (BRD)

  - Requirements Traceability Matrix (RTM)

- Conduct periodic reviews and walkthroughs

- Formal sign-offs at each milestone

WBS diagram