## Sheet1
WBS ID | Task Name | Description | Level | Owner | Start Date | End Date | Duration (Days) | Dependencies | Milestone (Yes/No) | Status
1 | HealthFirst Care Improvement Initiative | Project Root | 1 |  |  |  | 0 |  | No | Not Started
1.1 | Requirements Gathering | Phase | 2 |  |  |  | 0 |  | No | Not Started
1.1.1 | Conduct stakeholder interviews | Collect requirements from stakeholders | 3 |  |  |  | 0 |  | No | Not Started
1.1.2 | Analyze appointment data | Review scheduling and wait times | 3 |  |  |  | 0 | 1.1.1 | No | Not Started
1.1.3 | Review current workflows | Document existing processes | 3 |  |  |  | 0 | 1.1.1 | No | Not Started
1.1.4 | Document BRD | Business Requirements Document | 3 |  |  |  | 0 | 1.1.2,1.1.3 | Yes | Not Started
1.2 | Solution Design | Phase | 2 |  |  |  | 0 | 1.1.4 | No | Not Started
1.2.1 | Design scheduling workflow | Optimized scheduling process | 3 |  |  |  | 0 |  | No | Not Started
1.2.2 | Design system architecture | System integration design | 3 |  |  |  | 0 |  | No | Not Started
1.2.3 | Design dashboards | Resource tracking dashboards | 3 |  |  |  | 0 |  | No | Not Started
1.2.4 | Design notification system | SMS/Email alerts | 3 |  |  |  | 0 |  | No | Not Started
1.3 | Development | Phase | 2 |  |  |  | 0 | 1.2 | No | Not Started
1.3.1 | Develop scheduling module | Automation of appointments | 3 |  |  |  | 0 |  | No | Not Started
1.3.2 | Develop dashboards | Build analytics dashboards | 3 |  |  |  | 0 |  | No | Not Started
1.3.3 | Develop notification system | Real-time alerts system | 3 |  |  |  | 0 |  | No | Not Started
1.3.4 | System integration | Integrate hospital systems | 3 |  |  |  | 0 |  | No | Not Started
1.4 | Testing | Phase | 2 |  |  |  | 0 | 1.3 | No | Not Started
1.4.1 | Unit testing | Test individual components | 3 |  |  |  | 0 |  | No | Not Started
1.4.2 | System testing | End-to-end testing | 3 |  |  |  | 0 |  | No | Not Started
1.4.3 | User Acceptance Testing | UAT with stakeholders | 3 |  |  |  | 0 |  | Yes | In Progress
1.5 | Deployment | Phase | 2 |  |  |  | 0 | 1.4.3 | No | Not Started
1.5.1 | Deployment planning | Prepare rollout plan | 3 |  |  |  | 0 |  | No | Not Started
1.5.2 | Production rollout | Go-live execution | 3 |  |  |  | 0 |  | Yes | Not Started
1.5.3 | Go-live support | Post-deployment support | 3 |  |  |  | 0 |  | No | Not Started
1.6 | Training & Change Management | Phase | 2 |  |  |  | 0 | 1.5 | No | Not Started
1.6.1 | Create training materials | User guides and docs | 3 |  |  |  | 0 |  | No | Not Started
1.6.2 | Conduct training sessions | Train hospital staff | 3 |  |  |  | 0 |  | Yes | Not Started
1.7 | Monitoring & Optimization | Phase | 2 |  |  |  | 0 | 1.6 | No | Not Started
1.7.1 | Monitor performance | Track KPIs | 3 |  |  |  | 0 |  | No | Not Started
1.7.2 | Continuous improvement | System enhancements | 3 |  |  |  | 0 |  | No | Not Started
1.7.3 | Project closure | Final review and sign-off | 3 |  |  |  | 0 |  | Yes | Not Started